Supporting Authorities Group Meeting

MINUTES - 2pm: 05/11/2025

Chair: Don Baker

ATTENDEES

WSCC

ESCC

Wayforward

Natural England

South Downs NPA

Sussex Local Nature Partnership

Wealden DC

Chichester DC

Lewes & Eastbourne Councils

Mid Sussex DC

Brighton and Hove City Council

Crawley BC

Horsham DC

Rother DC

Adur & Worthing Councils

Arun DC

Hastings BC

- Introduction, Apologies, Matters arising – DB

  - Rebecca Fry HDC – Linsey King will represent HDC

  - Jennifer Hollingham MDSX

  - Anna Clare from LEC: but Jane Goodall is representing

  - A moment of silence was held in memory of Helen Peacock

- General update – DB

  - The public consultation began on target: 15 October and will close 26 November.

  - To support that we have initiated a comms strategy.  [picked up in the next agenda item from Wayforward – refer to attached notes: Agenda Item 3]  Request made for all SAG members to amplify the comms around the public consultation so we get the most comprehensive feedback possible.  Thanks to the amplification already undertaken.

  - Defra:

    - have written to us last week to congratulate us on crossing this milestone and have triggered the release of transition funding to support the process required to get us through to the delivery phase.

    - We will be meeting with Defra next week to discuss this further

  - Pre-Publication SAG Approval. Thank you for seeking & confirming the delegated authority to approve the pre-public Consultation draft.  There was some unavoidable internal governance to manage, consequently, we will shortly be asking the same question of you to confirm that you have delegated authority to approve the pre-publication draft and that any additional internal governance is possible to complete within the 28 day deadline.

    - We will do our best to give you a timeline but we will never be in a position to confirm our dates until a few weeks before. So any interaction with planned committee dates will be difficult to manage at your end.

  - Timing: An estimated timeline puts SA pre-publication early/mid-Feb and Publication March end 2026 (TBC).

- Public Consultation – what we’ve learnt so far - DA

- Open Session (matters arising from the LNRS Public consultation) – ALL

Confirmed TV interview is Latest TV.

NE Local team would like to use the bus-stop advert. Have we had any breakdown of stakeholders yet?

A: Not known as yet. Relatively few emails, mainly from landowners/advisors. Map comments, relatively even spread across three main user groups.

Comms assets next week, will that include video?

A: Video already shared. Has been shared with as many people as possible. For SDNPA, please email comms assets directly to Ruth.James@southdowns.gov.uk and Comms Team <CommsTeam@southdowns.gov.uk>.

Is there quite an spread across East and West?

A: Slightly more from West but fairly even at the moment.

Further amendments can be expected from some Supporting Authorities

Are the RAs expecting a formal response from the Supporting Authorities as part of the public consultation?

A: This decision is for the SAs.  You may wish to reiterate previous comments or add more but there is no requirement to do so.

What happened to the SA’s responses to the pre-publication draft

- The log is attached below

- AOB

  - There were no items of AOB